## Gantt Chart
ITL Enabler 4 Project Plan
PROJECT TITLE |  | ITL Enabler 4 |  |  |  |  | COMPANY NAME | [6 empty] | Integration Technologies Limited
PROJECT MANAGER |  | Jacob Copeland |  |  |  |  | COMMENCEMENT DATE | [6 empty] | 2019-07-15
* The team worked through the semester break. Therefore, for example, Week 8 of the course is actually Week 10 of this project.
GITHUB ISSUE NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | SPRINT ONE | [19 empty] | SPRINT TWO | [14 empty] | SPRINT THREE | [14 empty] | SPRINT FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7* |  |  |  |  | WEEK 8* |  |  |  |  | WEEK 9* |  |  |  |  | WEEK 10* |  |  |  |  | WEEK 11* |  |  |  |  | WEEK 12* |  |  |  |  | WEEK 13*
[7 empty] | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11
Project Conception and Planning
| Formation of team | All |  |  | 5 | 100% | bar: WEEK 1 15 to WEEK 1 19
| Liasing with client, project analysis | All |  |  | 5 | 100% | bar: WEEK 2 22 to WEEK 2 26
| Project planning | All |  |  | 5 | 100% | bar: WEEK 3 29 to WEEK 4 8
Sprint 1
1 | Installer return code comment lines | Jamie |  |  | 1 | 100% | bar: WEEK 3 2
2 | Create install log | Jamie |  |  | 2 | 100% | bar: WEEK 3 2 to WEEK 4 5
34 | Create two wizard pages | Jamie |  |  | 3 | 100% | bar: WEEK 4 6 to WEEK 4 8
| Install input folder during client install | Jamie |  |  | 2 | 100% | bar: WEEK 4 8 to WEEK 4 9
| Run an executable during server install | Jamie |  |  | 1 | 100% | bar: WEEK 4 9
Milestone 1 - New Release for Week 4 Demonstration (Release v0.1)
Sprint 2
3 | Set Installer Variables | Ricky |  |  | 11 | 100% | bar: WEEK 4 5 to WEEK 6 19
4 | Set command line options | Jacob |  |  | 15 | 100% | bar: WEEK 4 9 to WEEK 7* 29
5 | Startup processing | Ricky |  |  | 12 | 100% | bar: WEEK 5 14 to WEEK 7* 29
7 | Return from a restart | Ricky |  |  | 13 | 100% | bar: WEEK 5 14 to WEEK 7* 30
25 | Install security components | Jacob |  |  | 1 | 100% | bar: WEEK 5 16
26 | Install third party dlls | Jacob |  |  | 1 | 100% | bar: WEEK 5 16
28 | Install user docs | Jacob |  |  | 11 | 100% | bar: WEEK 5 16 to WEEK 7* 30
10 | Check disk space | Jacob |  |  | 6 | 100% | bar: WEEK 6 21 to WEEK 7* 28
20 | Remove variables in registry | Jacob |  |  | 7 | 100% | bar: WEEK 6 21 to WEEK 7* 29
21 | Install Enabler files | Jacob |  |  | 7 | 100% | bar: WEEK 6 21 to WEEK 7* 29
22 | Create licenses | Jacob |  |  | 6 | 100% | bar: WEEK 6 21 to WEEK 7* 28
23 | Setup environment variables & reg keys | Jacob |  |  | 7 | 100% | bar: WEEK 6 22 to WEEK 7* 30
29 | Update system config | Jacob |  |  | 5 | 100% | bar: WEEK 6 22 to WEEK 7* 28
31 | Add uninstall items | Jacob |  |  | 6 | 100% | bar: WEEK 6 22 to WEEK 7* 29
32 | Reboot system | Jacob |  |  | 7 | 100% | bar: WEEK 6 22 to WEEK 7* 30
Milestone 2 - Client Install 50% Complete (Release v0.2)
Sprint 3
9 | Get file system values | Jamie |  |  | 11 | 100% | bar: WEEK 6 19 to WEEK 8* 2
13 | Install .Net 3.5 | Jamie |  |  | 6 | 100% | bar: WEEK 8* 2 to WEEK 9* 9
14 | Install .Net 4 | Jamie |  |  | 4 | 100% | bar: WEEK 9* 9 to WEEK 9* 12
| Write client test schedule | Jamie |  |  | 6 | 100% | bar: WEEK 9* 13 to WEEK 10* 20
Milestone 3 - New Release for Week 8 Demonstration (Release v0.3)
Sprint 4
11 | Save config settings | Jacob |  |  | 25 | 90% | bar: WEEK 6 21 to WEEK 11* 24
24 | Install API assemblies | Jacob |  |  | 24 | 90% | bar: WEEK 6 22 to WEEK 11* 24
30 | Setup access permissions | Ricky |  |  | 24 | 90% | bar: WEEK 6 22 to WEEK 11* 24
19 | Install C++ Redistributables | Jacob |  |  | 12 | 90% | bar: WEEK 9* 9 to WEEK 11* 24
Various | Fix outstanding Client Install bugs | Jamie |  |  | 2 | 0% | bar: WEEK 11* 23 to WEEK 11* 24
| Onsite Client Install Test | Jacob/Ricky |  |  | 1 | 0% | bar: WEEK 11* 25
Various | Fix bugs found during Client Install test | Jamie/Jacob |  |  | 4 | 0% | bar: WEEK 11* 26 to WEEK 12* 1
Milestone 4 - Client Install Complete (Release v0.4)
6 | SQL Setup | Giovanni |  |  | 40 | ? | bar: WEEK 4 5 to WEEK 11* 27
27 | Install server files | Ricky |  |  | 12 | 0% | bar: WEEK 9* 12 to WEEK 11* 27
12 | MSI 4.5 Installer | Giovanni |  |  | 10 | 90% | bar: WEEK 10* 16 to WEEK 11* 27
15 | Service Pack install | Giovanni |  |  | 10 | 90% | bar: WEEK 10* 16 to WEEK 11* 27
16 | Server components install | Giovanni |  |  | 10 | 10% | bar: WEEK 10* 16 to WEEK 11* 27
17 | SQL Server blank password checks | Giovanni |  |  | 10 | 90% | bar: WEEK 10* 16 to WEEK 11* 27
18 | Install SQL Server | Giovanni |  |  | 10 | 0% | bar: WEEK 10* 16 to WEEK 11* 27
| Write server test schedule | Giovanni |  |  | 2 | 0% | bar: WEEK 12* 30 to WEEK 12* 1
| Onsite Full Install Test (date TBC) | Jacob/Ricky |  |  | 2 | 0% | bar: WEEK 12* 2 to WEEK 12* 3
Various | Fix bugs found during full test | All |  |  | 2 | 0% | bar: WEEK 12* 4 to WEEK 13* 7
| Onsite Full Install Test (date TBC) | Jacob/Ricky |  |  | 2 | 0% | bar: WEEK 13* 8 to WEEK 13* 9
| Tag final Release v1.0 | Jacob |  |  | 1 | 0% | bar: WEEK 13* 10
Milestone 5 - Full Install Complete (Release v1.0)
| Complete project documentation | All |  |  | 2 | 0% | bar: WEEK 13* 10 to WEEK 13* 11
Milestone 6 - Project Complete